## Sheet1
Phase | Date | Days taken(working) | Instructions
SRS signoff | 2016-12-21 | NAN
wireframes sent | 2016-12-27 | 4
wireframe signoff with two tiny questions | 2016-12-28 | 1
Database and backend architectural finalization |  |  | 50 to 60 % done
!!!!Work will stop at the next step if no 50% payment is done!!!!
backend logic layer work call stubs creation |  |  | MOST IMPORTANT THING WILL NEVER BE RUSHED--visual changes possible on normal cost of time and money. Functional changes on huge cost of time and money.
Backend pure dynamic logic and data access layer |  |  | parellel work -- unlimited period will go on in all sprints once started till the end
Front end Designing start -web app and IOS |  |  | parellel work -- limited period 1-2 week--changes will cost huge amount of time and money
front end designing start for android |  |  | parellel work -- limited period 1-2 week--changes will cost huge amount of time and money
Ios app, android app and web app development |  |  | parellel work -- unlimited period will go on in all sprints once started till the 80% time of the whole project exosted--very very small only TEXONOMY changes possibel on huge cost of time and money
Initigration testing |  |  | will Strat after the front ends and back end all completed or project 80%-- no change possible. 1 to 3 defects fixing possible. Bug fixing will happen
deployment testing |  |  | Last crutial 10% of the app never parellel and any change or defect discovered at this stage means full project faliur. Only small bugs and deployment issues can be solved.